## Scope (Quantity)
Scope What is in scope (features, functionality, integrations) and what is out of scope. We define risk profiles transparently. This visibility helps to allocate resources effectively, avoid unmanageable scope creep, and ultimately create a shared commitment. * Prices are all-in, meaning they include project management and end-to-end delivery of the product. Prices are ex. VAT. | MoSCoW Must Have Should Have Could Have Won't Have (out of scope) | Risk Profile Low (Proven) Moderate (Experimental) High (Dependant) | Notes | Proven Low risk profile. Price is fixed. Scope is clear and we own this work. | Price Fixed | Experimental Moderate risk profile. Price can be 30% lower or higher but never more. We share the risk when the work is experimental. | Price Minimum | Price Maximum | Dependant High risk profile. Price is estimation, but will be pay-by-hour. We depend on to-be-delivered APIs or externally employed team members. | Price Estimate, but will be pay-by-hour. Our rate on 05-02-2025 is €127,16/h - 25% discount.
[EPIC] v3.1 Widget Redesign (AITW-419)
[EPIC] v3 Widget Design Improvements (AITW-418)
└─ Repetitive Flashcard & Quiz titles (AITW-423) | Could Have | Proven | Story Points: 0 | 0 | 0
└─ Adjust title, text variants & spacing (AITW-422) | Could Have | Proven | Story Points: 0 | 0 | 0
└─ Add outline on default-state button (AITW-421) | Could Have | Proven | Story Points: 0 | 0 | 0
└─ Increase spacing between unit title and content below (AITW-420) | Could Have | Proven | Story Points: 0 | 0 | 0
└─ Change loading message for Flaschards & Quiz me (AITW-414) | Could Have | Proven | Story Points: 0 | 0 | 0
[EPIC] post-v Highlighter (AITW-362)
└─ As a student I want to be able to undo a highlight (AITW-368) | Could Have | Proven | Story Points: 0 | 0 | 0
└─ As a student I want to have easy access to the highlighter when available (AITW-367) | Could Have | Proven | Story Points: 0 | 0 | 0
└─ As a student, to highlight the most important parts of a summary made by Tutor AI, so I can focus on key concepts while studying. (AITW-366) | Could Have | Proven | Story Points: 0 | 0 | 0
[EPIC] post-v Learning path (AITW-361)
└─ As a student, I want the learning path to be adjusted based on my performance or missed sessions, so the plan remains updated and adapts to my schedule/preferences. (AITW-372) | Could Have | Proven | Story Points: 0 | 0 | 0
└─ As a student, I want to be able to track my progress within the learning path to stay motivated and know how far I am into my programme. (AITW-371) | Could Have | Proven | Story Points: 0 | 0 | 0
└─ As a student, I want to have milestones in my learning path, that will help me reinforce my understanding of key concepts before an exam or deadline (AITW-370) | Could Have | Proven | Story Points: 0 | 0 | 0
└─ As a student, I want to determine my learning goals, and have Tutor AI generate a feasible plan that allows me to fulfill these (AITW-369) | Could Have | Proven | Story Points: 0 | 0 | 0
[EPIC] v3.1 Saving answers (AITW-360)
└─ As a student I want to be able to go over my answers on previous quizzes (AITW-388) | Could Have | Proven | Story Points: 0 | 0 | 0
└─ As a student I need my responses to be saved in real time and to still be accesible after logging out and logging back in. (AITW-374) | Could Have | Proven | Story Points: 0 | 0 | 0
└─ As a student, I want all answers generated by Tutor AI to be saved automatically, so I don’t lose work when closing the widget. (AITW-373) | Could Have | Proven | Story Points: 0 | 0 | 0
[EPIC] v3.1 Chat history (AITW-359)
└─ As a student I want to have access to my chat history in order to consult old requests and answers (AITW-376) | Could Have | Proven | Story Points: 0 | 0 | 0
└─ As a student, I want to see the chat history from my last session, to continue my learning without losing progress. (AITW-375) | Could Have | Proven | Story Points: 0 | 0 | 0
[EPIC] v3 Widget Compatibility (AITW-358)
└─ As a user I want to have a seamless experience using Tutor AI regardless of which device I am accessing the widget from (AITW-381) | Could Have | Proven | Story Points: 0 | 0 | 0
└─ As a user I want to be able to access Tutor AI from multiple devices and breakpoints, mobile, desktop, iOS, Android, etc (AITW-380) | Could Have | Proven | Story Points: 0 | 0 | 0
[EPIC] v3.1 Personalization (AITW-357)
└─ As a student I want to be able to edit and adjust my settings and preference therefore affecting my answers (AITW-379) | Could Have | Proven | Story Points: 0 | 0 | 0
└─ As a student I want Tutor AI to make suggestions based on my profile, history and preferences (AITW-378) | Could Have | Proven | Story Points: 0 | 0 | 0
└─ As a student, I want the AI tutor to personalize its answers and examples to my knowledge and personal profile (e.g., beginner, intermediate, has dyslexia, ADHD,etc), so the content matches my understanding. (AITW-377) | Could Have | Proven | Story Points: 0 | 0 | 0
[EPIC] v3 Slow request time (AITW-356)
└─ As a student I'd like to be able to access a request that is loading easily and seamlessly (AITW-386) | Could Have | Proven | Story Points: 0 | 0 | 0
└─ As a student I'd like to have the possibility to cancel a request if I change my mind (AITW-385) | Could Have | Proven | Story Points: 0 | 0 | 0
└─ As a student I'd like to have loading indicators with estimated time left (AITW-384) | Could Have | Proven | Story Points: 0 | 0 | 0
└─ As a student, I want to receive a notification when TutorAI has finished processing my request for time optimization and a seamless experience (AITW-383) | Could Have | Proven | Story Points: 0 | 0 | 0
└─ As a student, I want to receive clear feedback (e.g. loader, message) when the TutorAI is processing my request to avoid frustration (AITW-382) | Could Have | Proven | Story Points: 0 | 0 | 0
[EPIC] v3 Mobile app (AITW-355)
└─ Diagram download feature (AITW-394) | Could Have | Proven | Story Points: 0 | 0 | 0
└─ Download podcast feature mobile (AITW-392) | Could Have | Proven | Story Points: 0 | 0 | 0
└─ Availabiliity on educa pro app (AITW-389) | Must Have | Proven | Story Points: 0 | 0 | 0
└─ Setup testing workflow (AITW-365) | Must Have | Proven | Story Points: 0 | 0 | 0
└─ User interface for mobile users (AITW-364) | Won't Have | Proven | Story Points: 0 | 0 | 0
└─ Availabillity on the ec-base monorepo (AITW-363) | Must Have | Dependant | Story Points: 0 | [5 empty] | 0 | 0
PROJECT SUMMARY
Total Epics: 10
Total Stories: 33
Total Story Points: 0
COST SUMMARY:
ESTIMATED TOTAL (worst case): | [9 empty] | €0.00

## Definition of Done (Quality)
Definition of Done | MoSCoW | Price Impact | Price Impact %
Code quality & documentation | Must Have |  | 0.04
Code is reviewed and approved via pull requests | Must Have |  | 0.025
Code is well-documented | Should Have |  | 0.04
Performance optimization | Should Have |  | 0.065
Testing & Cross-browser compatibility | Must Have |  | 0.065
Security vulnerabilities are identified | Must Have |  | 0.04

## Settings
Settings
Range for Experimental pricing (up & down) | 0.3
Base price of 8 story points | 1040
Base price of 1 story point | 130
Hourly rate | 95.37