## Scope (Quantity)
Scope What is in scope (features, functionality, integrations) and what is out of scope. We define risk profiles transparently. This visibility helps to allocate resources effectively, avoid unmanageable scope creep, and ultimately create a shared commitment. * Prices are all-in, meaning they include project management and end-to-end delivery of the product. Prices are ex. VAT. | MoSCoW Must Have Should Have Could Have Won't Have (out of scope) | Risk Profile Low (Proven) Moderate (Experimental) High (Dependant) | Notes | Proven Low risk profile. Price is fixed. Scope is clear and we own this work. | Price Fixed | Experimental Moderate risk profile. Price can be 30% lower or higher but never more. We share the risk when the work is experimental. | Price Minimum | Price Maximum | Dependant High risk profile. Price is estimation, but will be pay-by-hour. We depend on to-be-delivered APIs or externally employed team members. | Price Estimate, but will be pay-by-hour. Our rate on 05-02-2025 is €127,16/h - 25% discount.
[EPIC] v3 Mobile app (AITW-355)
└─ Diagram download feature (AITW-394) | Could Have | Proven | Story Points: 0 | 0 | 0
└─ Download podcast feature mobile (AITW-392) | Could Have | Proven | Story Points: 0 | 0 | 0
└─ Availabiliity on educa pro app (AITW-389) | Must Have | Proven | Story Points: 0 | 0 | 0
└─ Setup testing workflow (AITW-365) | Must Have | Proven | Story Points: 0 | 0 | 0
└─ User interface for mobile users (AITW-364) | Won't Have | Proven | Story Points: 0 | 0 | 0
└─ Availabillity on the ec-base monorepo (AITW-363) | Must Have | Dependant | Story Points: 0 | [5 empty] | 0 | 0
PROJECT SUMMARY - v3
Total Epics: 1
Total Stories: 6
Total Story Points: 0
COST SUMMARY:
ESTIMATED TOTAL (worst case): | [9 empty] | €0.00

## Definition of Done (Quality)
Definition of Done | MoSCoW | Price Impact | Price Impact %
Code quality & documentation | Must Have |  | 0.04
Code is reviewed and approved via pull requests | Must Have |  | 0.025
Code is well-documented | Should Have |  | 0.04
Performance optimization | Should Have |  | 0.065
Testing & Cross-browser compatibility | Must Have |  | 0.065
Security vulnerabilities are identified | Must Have |  | 0.04

## Settings
Settings
Range for Experimental pricing (up & down) | 0.3
Base price of 8 story points | 1040
Base price of 1 story point | 130
Hourly rate | 95.37

## Sprint Planning
Sprint Planning & Team Composition Analysis
Project Overview
Total Story Points: | 0
Number of Epics: | 1
Epic Breakdown
Epic Key | Summary | Story Points | Story Count
AITW-355 | v3 Mobile app | 0 | 6
Team Composition Comparison
| Team Size | Total FTE | Velocity (SP/sprint) | Sprints Needed | Weeks | Months
Small | 3 | 2.5 | 13.6 | 0 | 0 | 0.0
Medium | 5 | 5.5 | 33.1 | 0 | 0 | 0.0
Large | 7 | 10.5 | 59.1 | 0 | 0 | 0.0
Risk Profile Analysis
Risk Profile | Stories | Story Points | % of Stories | % of Story Points
Proven | 5 | 0 | 83.3% | 0.0%
Experimental | 0 | 0 | 0.0% | 0.0%
Dependant | 1 | 0 | 16.7% | 0.0%
Recommendations
1. Small project - single developer might be sufficient